## Sheet1
Task | Week 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Project start |  | V
Choose project |  |  |  | V
Complete project contract
Literature review | [6 empty] | V
Requirements specification | [6 empty] | V
First submission | [7 empty] | V
Write app | [11 empty] | V
Holiday | [14 empty] | V
Write app
Test app | [19 empty] | V
Write final report
Holiday
Write final report | [28 empty] | V
Second submission
Viva
Key: V is move to next task
Research/writing:
Writing app:
Deliverable:
Holiday: